## Project Data
Project Name | Task Name | Assigned To | Start Date | Days Required | End Date | Progress | Progress % | Status | Duration (Days) | Schedule Variance | On Track | Month Started
Marketing | Market Research | Alice | 2024-01-01 | 13 | 2024-01-14 | 78% | 78 | In Progress | 13 | -22% | At Risk | Jan 2024
Marketing | Content Creation | Bob | 2024-01-14 | 14 | 2024-01-28 | 100% | 100 | Completed | 14 | 0% | On Track | Jan 2024
Marketing | Social Media Planning | Charlie | 2024-01-28 | 22 | 2024-02-19 | 45% | 45 | In Progress | 22 | -55% | Behind Schedule | Jan 2024
Marketing | Campaign Analysis | Daisy | 2024-02-18 | 25 | 2024-03-14 | 0% | 0 | Not Started | 25 | -100% | Behind Schedule | Feb 2024
Product Dev | Prototype Development | Ethan | 2024-01-02 | 18 | 2024-01-20 | 100% | 100 | Completed | 18 | 0% | On Track | Jan 2024
Product Dev | Quality Assurance | Fiona | 2024-01-20 | 10 | 2024-01-30 | 78% | 78 | In Progress | 10 | -22% | At Risk | Jan 2024
Product Dev | User Interface Design | Gabriel | 2024-02-04 | 25 | 2024-02-29 | 0% | 0 | Not Started | 25 | -100% | Behind Schedule | Feb 2024
Customer Svc | Service Improvement | Hannah | 2024-02-01 | 22 | 2024-02-23 | 100% | 100 | Completed | 22 | 0% | On Track | Feb 2024
Customer Svc | Ticket Resolution | Ian | 2024-02-24 | 25 | 2024-03-20 | 100% | 100 | Completed | 25 | 0% | On Track | Feb 2024
Customer Svc | Customer Feedback | Julia | 2024-03-21 | 30 | 2024-04-20 | 0% | 0 | Not Started | 30 | -100% | Behind Schedule | Mar 2024
Financial | Budget Analysis | Kevin | 2024-02-02 | 22 | 2024-02-24 | 10% | 10 | In Progress | 22 | -90% | Behind Schedule | Feb 2024
Financial | Financial Reporting | Mark | 2024-02-13 | 21 | 2024-02-09 | 78% | 78 | In Progress | -4 | 1753% | On Track | Feb 2024
Financial | Investment Planning | Mark | 2024-03-19 | 25 | 2024-04-13 | 100% | 100 | Completed | 25 | 0% | On Track | Mar 2024
Research | Market Trends Analysis | Nathan | 2024-01-02 | 23 | 2024-01-25 | 50% | 50 | In Progress | 23 | -50% | Behind Schedule | Jan 2024
Research | Data Collection | Olivia | 2024-01-26 | 32 | 2024-02-27 | 0% | 0 | Not Started | 32 | -100% | Behind Schedule | Jan 2024
Research | Research Paper Writing | Peter | 2024-02-28 | 27 | 2024-03-26 | 0% | 0 | Not Started | 27 | -100% | Behind Schedule | Feb 2024
Development | Software Development | Quinn | 2024-01-02 | 36 | 2024-02-07 | 100% | 100 | Completed | 36 | 0% | On Track | Jan 2024
Development | Feature Enhancement | Rachel | 2024-02-08 | 34 | 2024-03-13 | 0% | 0 | Not Started | 34 | -100% | Behind Schedule | Feb 2024
Development | Code Review | Sam | 2024-03-14 | 30 | 2024-04-13 | 0% | 0 | Not Started | 30 | -100% | Behind Schedule | Mar 2024
Production | Manufacturing | Tim | 2024-01-03 | 47 | 2024-02-19 | 30% | 30 | In Progress | 47 | -70% | Behind Schedule | Jan 2024
Production | Quality Control | Ursula | 2024-02-17 | 27 | 2024-03-15 | 0% | 0 | Not Started | 27 | -100% | Behind Schedule | Feb 2024
Production | Packaging Design | Victor | 2024-03-14 | 22 | 2024-04-05 | 0% | 0 | Not Started | 22 | -100% | Behind Schedule | Mar 2024
Sales | Lead Generation | Wendy | 2024-01-03 | 60 | 2024-03-03 | 70% | 70 | In Progress | 60 | -30% | Behind Schedule | Jan 2024
Sales | Client Meetings | Xavier | 2024-01-06 | 20 | 2024-01-26 | 78% | 78 | In Progress | 20 | -22% | At Risk | Jan 2024
Sales | Contract Negotiation | Yvette | 2024-02-03 | 35 | 2024-03-09 | 0% | 0 | Not Started | 35 | -100% | Behind Schedule | Feb 2024
Support | Technical Support | Zoe | 2024-01-01 | 25 | 2024-01-26 | 100% | 100 | Completed | 25 | 0% | On Track | Jan 2024
Support | Bug Fixes | Aaron | 2024-01-27 | 31 | 2024-02-27 | 100% | 100 | Completed | 31 | 0% | On Track | Jan 2024
Support | Software Updates | Bella | 2024-03-02 | 22 | 2024-03-24 | 0% | 0 | Not Started | 22 | -100% | Behind Schedule | Mar 2024
Operations | Process Optimization | Calvin | 2024-01-03 | 30 | 2024-02-02 | 40% | 40 | In Progress | 30 | -60% | Behind Schedule | Jan 2024
Operations | Inventory Management | Diane | 2024-02-03 | 25 | 2024-02-28 | 0% | 0 | Not Started | 25 | -100% | Behind Schedule | Feb 2024
Operations | Facility Maintenance | Edward | 2024-02-29 | 20 | 2024-03-20 | 0% | 0 | Not Started | 20 | -100% | Behind Schedule | Feb 2024
Consulting | Strategic Planning | Fiona | 2024-01-02 | 35 | 2024-02-06 | 60% | 60 | In Progress | 35 | -40% | Behind Schedule | Jan 2024
Consulting | Market Expansion | Gary | 2024-02-02 | 32 | 2024-03-05 | 0% | 0 | Not Started | 32 | -100% | Behind Schedule | Feb 2024
Consulting | Client Advisory | Helen | 2024-03-06 | 25 | 2024-03-31 | 0% | 0 | Not Started | 25 | -100% | Behind Schedule | Mar 2024
Training | Employee Training | Isaac | 2024-01-04 | 27 | 2024-01-31 | 80% | 80 | In Progress | 27 | -20% | At Risk | Jan 2024
Training | Certification Programs | Jane | 2024-01-28 | 30 | 2024-02-27 | 0% | 0 | Not Started | 30 | -100% | Behind Schedule | Jan 2024
Training | Skill Development | Kyle | 2024-02-28 | 22 | 2024-03-21 | 0% | 0 | Not Started | 22 | -100% | Behind Schedule | Feb 2024
Events | Event Planning | Laura | 2024-01-03 | 25 | 2024-01-28 | 30% | 30 | In Progress | 25 | -70% | Behind Schedule | Jan 2024
Events | Conference Management | Mike | 2024-02-03 | 20 | 2024-02-23 | 0% | 0 | Not Started | 20 | -100% | Behind Schedule | Feb 2024
Events | Sponsorship Coordinatio | n Nancy | 2024-02-24 | 35 | 2024-03-30 | 0% | 0 | Not Started | 35 | -100% | Behind Schedule | Feb 2024
Logistics | Supply Chain Management | Oscar | 2024-01-03 | 25 | 2024-01-28 | 50% | 50 | In Progress | 25 | -50% | Behind Schedule | Jan 2024
Logistics | Transportation Planning | Patricia | 2024-01-29 | 30 | 2024-02-28 | 100% | 100 | Completed | 30 | 0% | On Track | Jan 2024
Logistics | Inventory Optimization | Quentin | 2024-03-29 | 20 | 2024-04-18 | 0% | 0 | Not Started | 20 | -100% | Behind Schedule | Mar 2024
Engineering | Product Design | Rachel | 2024-01-02 | 25 | 2024-01-27 | 20% | 20 | In Progress | 25 | -80% | Behind Schedule | Jan 2024
Engineering | System Integration | Sam | 2024-02-02 | 22 | 2024-02-24 | 0% | 0 | Not Started | 22 | -100% | Behind Schedule | Feb 2024
Engineering | Prototype Testing | Tom | 2024-02-23 | 27 | 2024-03-21 | 0% | 0 | Not Started | 27 | -100% | Behind Schedule | Feb 2024

## KPI Summary
PROJECT MANAGEMENT KPIs
Priority-Ordered Key Performance Indicators
Priority | KPI Name | Value | Description
P1 - CRITICAL | Overall Completion Rate | 19.6% | Percentage of all tasks fully completed
P1 - CRITICAL | Average Task Progress | 36.9% | Mean progress across all 46 tasks
P1 - CRITICAL | Tasks Not Started | 22 (48%) | Tasks with zero progress - immediate action needed
P2 - HIGH | Total Tasks | 46 | Total scope of work
P2 - HIGH | Total Projects | 15 | Number of active projects
P2 - HIGH | Tasks Behind Schedule | 32 | Tasks significantly behind expected progress
P2 - HIGH | Tasks At Risk | 4 | Tasks moderately behind expected progress
P3 - MEDIUM | Project Completion by Dept | See breakdown | Per-project average completion percentage
P3 - MEDIUM | Total Team Members | 42 | Number of team members with assignments
P3 - MEDIUM | Avg Days per Task | 26 days | Average task duration in days
P4 - LOW | Total Effort | 1218 days | Sum of all task durations
P4 - LOW | Project Timeline Span | Jan 1 - Apr 20, 2024 (110 days) | Full project portfolio duration
P4 - LOW | Longest Task | 60 days (Lead Generation) | Most time-intensive task
P4 - LOW | Shortest Task | 10 days (Quality Assurance) | Quickest task

## Project Summary
PROJECT SUMMARY
Project Name | Total Tasks | Avg Progress | Completed | In Progress | Not Started | Total Days | Avg Days/Task | Start | End
Customer Svc | 3 | 66.67% | 2 | 0 | 1 | 77 | 25.7 | 2024-02-01 | 2024-04-20
Support | 3 | 66.67% | 2 | 0 | 1 | 78 | 26 | 2024-01-01 | 2024-03-24
Financial | 3 | 62.67% | 1 | 2 | 0 | 68 | 22.7 | 2024-02-02 | 2024-04-13
Product Dev | 3 | 59.33% | 1 | 1 | 1 | 53 | 17.7 | 2024-01-02 | 2024-02-29
Marketing | 4 | 55.75% | 1 | 2 | 1 | 74 | 18.5 | 2024-01-01 | 2024-03-14
Logistics | 3 | 50% | 1 | 1 | 1 | 75 | 25 | 2024-01-03 | 2024-04-18
Sales | 3 | 49.33% | 0 | 2 | 1 | 115 | 38.3 | 2024-01-03 | 2024-03-09
Development | 3 | 33.33% | 1 | 0 | 2 | 100 | 33.3 | 2024-01-02 | 2024-04-13
Training | 3 | 26.67% | 0 | 1 | 2 | 79 | 26.3 | 2024-01-04 | 2024-03-21
Consulting | 3 | 20% | 0 | 1 | 2 | 92 | 30.7 | 2024-01-02 | 2024-03-31
Research | 3 | 16.67% | 0 | 1 | 2 | 82 | 27.3 | 2024-01-02 | 2024-03-26
Operations | 3 | 13.33% | 0 | 1 | 2 | 75 | 25 | 2024-01-03 | 2024-03-20
Events | 3 | 10% | 0 | 1 | 2 | 80 | 26.7 | 2024-01-03 | 2024-03-30
Production | 3 | 10% | 0 | 1 | 2 | 96 | 32 | 2024-01-03 | 2024-04-05
Engineering | 3 | 6.667% | 0 | 1 | 2 | 74 | 24.7 | 2024-01-02 | 2024-03-21